## QTY Change Log
Line Item | SW62 - Centinela | Unit | QTY | Descoped | Delayed | Additional | PROJECTED TOTAL | Complete | Remaining | Notes
DEMO/EXCAVATION
1 | Sawcut | LF | 108 |  |  |  | 108 |  |  |  | 1878.33 | total SF
2 | Remove Concrete Curb & Gutter | LF | 134 |  |  |  | 134 |  |  |  | 1744.76
3 | Remove Concrete Sidewalk | SF | 1746.48 |  |  |  | 1746.48
4 | Remove Concrete Pavement | SF |  |  |  |  | 0
5 | Remove Asphalt Concrete Pavement | SF | 142.46 |  |  |  | 142.46
6 | Remove Concrete Driveway | SF | 131.85 |  |  |  | 131.85
7 | Remove Curb Ramp | SF |  |  |  |  | 0
31 | Excavation | CY |  |  |  |  | 0
31.1 | Remove Concrete Curb & Gutter | LF | 134 |  |  |  | 134
31.2 | Remove Concrete Sidewalk | SF | 1746.48 |  |  |  | 1746.48
31.3 | Remove Concrete Pavement | SF |  |  |  |  | 0
31.4 | Remove Asphalt Concrete Pavement | SF | 142.46 |  |  |  | 142.46
31.5 | Remove Concrete Driveway | SF | 131.85 |  |  |  | 131.85
31.6 | Remove Curb Ramp | SF |  |  |  |  | 0
| BASE/GRADING | [5 empty] | 0
8 | Base/Grading Curb and Gutter | LF | 134 |  |  |  | 134
9 | Base/Grading Concrete Curb | LF |  |  |  |  | 0
10 | Base/Grading Concrete Gutter | SF |  |  |  |  | 0
11 | Base/Grading Gutter and Pavement | SF |  |  |  |  | 0
12 | Base/Grading Concrete Pavement | SF |  |  |  |  | 0
13 | Base/Grading Concrete Sidewalk (4 in) | SF | 1746.48 |  |  |  | 1746.48
14 | Base/Grading Concrete Driveway (6 in) | SF | 131.85 |  |  |  | 131.85
15 | Base/Grading Curb Ramp | SF |  |  |  |  | 0
16 | Base/Grading AC Pavement | SF | 142.46 |  |  |  | 142.46
| CONCRETE | [5 empty] | 0
17 | Concrete Intergral Curb and Gutter | LF | 134 |  |  |  | 134
18 | Concrete Curb | LF |  |  |  |  | 0
19 | Concrete Gutter | SF |  |  |  |  | 0
20 | Gutter and Pavement | SF |  |  |  |  | 0
21 | Concrete Pavement | SF |  |  |  |  | 0
22 | Concrete Sidewalk (4 in) | SF | 1746.48 |  |  |  | 1746.48
23 | Concrete Driveway (6 in) | SF | 131.85 |  |  |  | 131.85
24 | Curb Ramp | SF |  |  |  |  | 0
| ASPHALT | [5 empty] | 0
25 | Asphalt Concrete Pavement | SF | 142.46 |  |  |  | 142.46
| Utility Adjustments | [5 empty] | 0
26 | Pull Box Replacement | EA |  |  |  |  | 0
27 | LADWP Vault Lids | EA | 1 |  |  |  | 1
32 | Pull Box Relocate and/or Adjust | EA |  |  |  |  | 0
| Landscaping | [5 empty] | 0
28 | Tree Stump Grind | EA |  |  |  |  | 0
29 | Bamboo Stump Grind | EA |  |  |  |  | 0
30 | Tree Trim and Root Prune | EA |  |  |  |  | 0
31 | Remove and Replace Street Sign | EA | 1 |  |  |  | 1

## Line Items
Line Item | SW62 - Centinela | Unit | QTY | Actuals | Unit Cost | Unit Total | Cost Code | UM | QTY | PX | HRS | LBR COST | EQUIP | TRUCKING | DUMP FEES | MATERIAL | SUB | BUDGET | BILLINGS
| DEMO/EXCAVATION | [16 empty] | 0 | 0
1 | Sawcut | LF | 108 |  |  | 0 | DEMO/EX | CY | 0.27 | 20 | 5.4 | [6 empty] | 0 | 0
2 | Remove Concrete Curb & Gutter | LF | 134 |  |  | 0 | DEMO/EX | CY | 8.9333 | 0.75 | 6.7 | [6 empty] | 0 | 0
3 | Remove Concrete Sidewalk | SF | 1746.48 |  |  | 0 | DEMO/EX | CY | 21.5615 | 0.75 | 16.1711 | [6 empty] | 0 | 0
4 | Remove Concrete Pavement | SF | 0 |  |  | 0 | DEMO/EX | CY | 0 | 0.75 | 0 | [6 empty] | 0 | 0
5 | Remove Asphalt Concrete Pavement | SF | 142.46 |  |  | 0 | DEMO/EX | CY | 2.6381 | 0.75 | 1.9786 | [6 empty] | 0 | 0
6 | Remove Concrete Driveway | SF | 131.85 |  |  | 0 | DEMO/EX | CY | 2.4417 | 0.75 | 1.8312 | [6 empty] | 0 | 0
7 | Remove Curb Ramp | SF | 0 |  |  | 0 | DEMO/EX | CY | 0 | 0.75 | 0 | [6 empty] | 0 | 0
31 | Excavation | CY | 30.4746 |  |  | 0 | DEMO/EX | CY | 35.5746 | 0.75 | 26.681 | [6 empty] | 0 | 0
31.1 | Remove Concrete Curb & Gutter | LF | 134 |  |  | 0 | DEMO/EX | CY | 8.9333 | 0.75 | 6.7 | [6 empty] | 0 | 0
31.2 | Remove Concrete Sidewalk | SF | 1746.48 |  |  | 0 | DEMO/EX | CY | 21.5615 | 0.75 | 16.1711 | [6 empty] | 0 | 0
31.3 | Remove Concrete Pavement | SF | 0 |  |  | 0 | DEMO/EX | CY | 0 | 0.75 | 0 | [6 empty] | 0 | 0
31.4 | Remove Asphalt Concrete Pavement | SF | 142.46 |  |  | 0 | DEMO/EX | CY | 2.6381 | 0.75 | 1.9786 | [6 empty] | 0 | 0
31.5 | Remove Concrete Driveway | SF | 131.85 |  |  | 0 | DEMO/EX | CY | 2.4417 | 0.75 | 1.8312 | [6 empty] | 0 | 0
31.6 | Remove Curb Ramp | SF | 0 |  |  | 0 | DEMO/EX | CY | 0 | 0.75 | 0 | [6 empty] | 0 | 0
| BASE/GRADING |  | 0 | [14 empty] | 0 | 0
8 | Base/Grading Curb and Gutter | LF | 134 |  |  | 0 | BASE/GRADING | CY | 8.9333 | 1 | 8.9333 | [6 empty] | 0 | 0
9 | Base/Grading Concrete Curb | LF | 0 |  |  | 0 | BASE/GRADING | CY | 0 | 1 | 0 | [6 empty] | 0 | 0
10 | Base/Grading Concrete Gutter | SF | 0 |  |  | 0 | BASE/GRADING | CY | 0 | 1 | 0 | [6 empty] | 0 | 0
11 | Base/Grading Gutter and Pavement | SF | 0 |  |  | 0 | BASE/GRADING | CY | 0 | 1 | 0 | [6 empty] | 0 | 0
12 | Base/Grading Concrete Pavement | SF | 0 |  |  | 0 | BASE/GRADING | CY | 0 | 1 | 0 | [6 empty] | 0 | 0
13 | Base/Grading Concrete Sidewalk (4 in) | SF | 1746.48 |  |  | 0 | BASE/GRADING | CY | 21.5615 | 1 | 21.5615 | [6 empty] | 0 | 0
14 | Base/Grading Concrete Driveway (6 in) | SF | 131.85 |  |  | 0 | BASE/GRADING | CY | 2.4417 | 1 | 2.4417 | [6 empty] | 0 | 0
15 | Base/Grading Curb Ramp | SF | 0 |  |  | 0 | BASE/GRADING | CY | 0 | 1 | 0 | [6 empty] | 0 | 0
16 | Base/Grading AC Pavement | SF | 142.46 |  |  | 0 | BASE/GRADING | CY | 2.6381 | 1 | 2.6381 | [6 empty] | 0 | 0
| CONCRETE |  | 0 | [14 empty] | 0 | 0
17 | Concrete Intergral Curb and Gutter | LF | 134 |  |  | 0 | CONCRETE | CY | 8.9333 | 6 | 53.6 | [6 empty] | 0 | 0
18 | Concrete Curb | LF | 0 |  |  | 0 | CONCRETE | CY | 0 | 6 | 0 | [6 empty] | 0 | 0
19 | Concrete Gutter | SF | 0 |  |  | 0 | CONCRETE | CY | 0 | 6 | 0 | [6 empty] | 0 | 0
20 | Gutter and Pavement | SF | 0 |  |  | 0 | CONCRETE | CY | 0 | 6 | 0 | [6 empty] | 0 | 0
21 | Concrete Pavement | SF | 0 |  |  | 0 | CONCRETE | CY | 0 | 6 | 0 | [6 empty] | 0 | 0
22 | Concrete Sidewalk (4 in) | SF | 1746.48 |  |  | 0 | CONCRETE | CY | 21.5615 | 6 | 129.3689 | [6 empty] | 0 | 0
23 | Concrete Driveway (6 in) | SF | 131.85 |  |  | 0 | CONCRETE | CY | 2.4417 | 6 | 14.65 | [6 empty] | 0 | 0
24 | Curb Ramp | SF | 0 |  |  | 0 | CONCRETE | CY | 0 | 6 | 0 | [6 empty] | 0 | 0
| ASPHALT |  | 0 | [14 empty] | 0 | 0
25 | Asphalt Concrete Pavement | SF | 142.46 |  |  | 0 | AC | TON | 5.4792 | 1 | 5.4792 | [6 empty] | 0 | 0
| Utility Adjustments |  | 0 | [14 empty] | 0 | 0
26 | Pull Box Replacement | EA | 0 |  |  | 0 | UTILITY ADJ | EA | 0 |  | 0 | [6 empty] | 0 | 0
27 | LADWP Vault Lids | EA | 1 |  |  | 0 | UTILITY ADJ | EA | 1 |  | 0 | [6 empty] | 0 | 0
32 | Pull Box Relocate and/or Adjust | EA | 0 |  |  | 0 | UTILITY ADJ | EA | 0 |  | 0 | [6 empty] | 0 | 0
| Landscaping |  | 0 | [14 empty] | 0 | 0
28 | Tree Stump Grind | EA | 0 |  |  | 0 | LANDSCAPING | EA | 0 |  | 0 | [6 empty] | 0 | 0
29 | Bamboo Stump Grind | EA | 0 |  |  | 0 | LANDSCAPING | EA | 0 |  | 0 | [6 empty] | 0 | 0
30 | Tree Trim and Root Prune | EA | 0 |  |  | 0 | LANDSCAPING | EA | 0 |  | 0 | [6 empty] | 0 | 0
31 | Remove and Replace Street Sign | EA | 1 |  |  | 0 | DEMO/EX | CY | 1 | 0.75 | 0.75 | [6 empty] | 0 | 0
| COST CODE | PX |  | ACTUAL HRS
| DEMO/EX | 20
| BASE/GRADING | 1
| CONCRETE | 6
| AC | 1
Update PX Rates
Create Final Reports

## Cost Code Breakdown
SW62 - Centinela
DEMO/EX
Line Item | SW62 - Centinela | Unit | QTY | Cost Code | CY | PX | HRS | MD | CREW SIZE | CREW DAYS
1 | Sawcut | LF | 108 | DEMO/EX | 0.27 | 20 | 5.4 | 0.675 |  | #DIV/0!
2 | Remove Concrete Curb & Gutter | LF | 134 | DEMO/EX | 8.9333 | 0.75 | 6.7 | 0.8375 |  | #DIV/0!
3 | Remove Concrete Sidewalk | SF | 1746.48 | DEMO/EX | 21.5615 | 0.75 | 16.1711 | 2.0214 |  | #DIV/0!
4 | Remove Concrete Pavement | SF | 0 | DEMO/EX | 0 | 0.75 | 0 | 0 |  | #DIV/0!
5 | Remove Asphalt Concrete Pavement | SF | 142.46 | DEMO/EX | 2.6381 | 0.75 | 1.9786 | 0.24733 |  | #DIV/0!
6 | Remove Concrete Driveway | SF | 131.85 | DEMO/EX | 2.4417 | 0.75 | 1.8312 | 0.22891 |  | #DIV/0!
7 | Remove Curb Ramp | SF | 0 | DEMO/EX | 0 | 0.75 | 0 | 0 |  | #DIV/0!
31.1 | Remove Concrete Curb & Gutter | LF | 134 | DEMO/EX | 8.9333 | 0.75 | 6.7 | 0.8375 |  | #DIV/0!
31.2 | Remove Concrete Sidewalk | SF | 1746.48 | DEMO/EX | 21.5615 | 0.75 | 16.1711 | 2.0214 |  | #DIV/0!
31.3 | Remove Concrete Pavement | SF | 0 | DEMO/EX | 0 | 0.75 | 0 | 0 |  | #DIV/0!
31.4 | Remove Asphalt Concrete Pavement | SF | 142.46 | DEMO/EX | 2.6381 | 0.75 | 1.9786 | 0.24733 |  | #DIV/0!
31.5 | Remove Concrete Driveway | SF | 131.85 | DEMO/EX | 2.4417 | 0.75 | 1.8312 | 0.22891 |  | #DIV/0!
31.6 | Remove Curb Ramp | SF | 0 | DEMO/EX | 0 | 0.75 | 0 | 0 |  | #DIV/0!
31 | Remove and Replace Street Sign | EA | 1 | DEMO/EX | 1 | 0.75 | 0.75 | 0.09375 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | DEMO/EX | 72.4193 |  | 59.5119 | 7.439 | #DIV/0! | #DIV/0!
BASE/GRADING
Line Item | SW62 - Centinela | Unit | QTY | Cost Code | CY | PX | HRS | MD | CREW SIZE | CREW DAYS
8 | Base/Grading Curb and Gutter | LF | 134 | BASE/GRADING | 8.9333 | 1 | 8.9333 | 1.1167 |  | #DIV/0!
9 | Base/Grading Concrete Curb | LF | 0 | BASE/GRADING | 0 | 1 | 0 | 0 |  | #DIV/0!
10 | Base/Grading Concrete Gutter | SF | 0 | BASE/GRADING | 0 | 1 | 0 | 0 |  | #DIV/0!
11 | Base/Grading Gutter and Pavement | SF | 0 | BASE/GRADING | 0 | 1 | 0 | 0 |  | #DIV/0!
12 | Base/Grading Concrete Pavement | SF | 0 | BASE/GRADING | 0 | 1 | 0 | 0 |  | #DIV/0!
13 | Base/Grading Concrete Sidewalk (4 in) | SF | 1746.48 | BASE/GRADING | 21.5615 | 1 | 21.5615 | 2.6952 |  | #DIV/0!
14 | Base/Grading Concrete Driveway (6 in) | SF | 131.85 | BASE/GRADING | 2.4417 | 1 | 2.4417 | 0.30521 |  | #DIV/0!
15 | Base/Grading Curb Ramp | SF | 0 | BASE/GRADING | 0 | 1 | 0 | 0 |  | #DIV/0!
16 | Base/Grading AC Pavement | SF | 142.46 | BASE/GRADING | 2.6381 | 1 | 2.6381 | 0.32977 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | BASE/GRADING | 35.5746 |  | 35.5746 | 4.4468 | #DIV/0! | #DIV/0!
CONCRETE
Line Item | SW62 - Centinela | Unit | QTY | Cost Code | CY | PX | HRS | MD | CREW SIZE | CREW DAYS
17 | Concrete Intergral Curb and Gutter | LF | 134 | CONCRETE | 8.9333 | 5 | 44.6667 | 5.5833 |  | #DIV/0!
18 | Concrete Curb | LF | 0 | CONCRETE | 0 | 5 | 0 | 0 |  | #DIV/0!
19 | Concrete Gutter | SF | 0 | CONCRETE | 0 | 5 | 0 | 0 |  | #DIV/0!
20 | Gutter and Pavement | SF | 0 | CONCRETE | 0 | 5 | 0 | 0 |  | #DIV/0!
21 | Concrete Pavement | SF | 0 | CONCRETE | 0 | 5 | 0 | 0 |  | #DIV/0!
22 | Concrete Sidewalk (4 in) | SF | 1746.48 | CONCRETE | 21.5615 | 5 | 107.8074 | 13.4759 |  | #DIV/0!
23 | Concrete Driveway (6 in) | SF | 131.85 | CONCRETE | 2.4417 | 5 | 12.2083 | 1.526 |  | #DIV/0!
24 | Curb Ramp | SF | 0 | CONCRETE | 0 | 5 | 0 | 0 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | CONCRETE | 32.9365 |  | 164.6824 | 20.5853 | #DIV/0! | #DIV/0!
AC
Line Item | SW62 - Centinela | Unit | QTY | Cost Code | TON | PX | HRS | MD | CREW SIZE | CREW DAYS
25 | Asphalt Concrete Pavement | SF | 142.46 | AC | 5.4792 | 1 | 5.4792 | 0.6849 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | AC | 5.4792 |  | 5.4792 | 0.6849 | #DIV/0! | #DIV/0!
UTILITY ADJ
Line Item | SW62 - Centinela | Unit | QTY | Cost Code | QTY | PX | HRS | MD | CREW SIZE | CREW DAYS
26 | Pull Box Replacement | EA | 0 | UTILITY ADJ | 0 |  | 0 | 0 |  | #DIV/0!
27 | LADWP Vault Lids | EA | 1 | UTILITY ADJ | 1 |  | 0 | 0 |  | #DIV/0!
32 | Pull Box Relocate and/or Adjust | EA | 0 | UTILITY ADJ | 0 |  | 0 | 0 |  | #DIV/0!
LANDSCAPING
Line Item | SW62 - Centinela | Unit | QTY | Cost Code | QTY | PX | HRS | MD | CREW SIZE | CREW DAYS
28 | Tree Stump Grind | EA | 0 | LANDSCAPING | 0 |  | 0 | 0 |  | #DIV/0!
29 | Bamboo Stump Grind | EA | 0 | LANDSCAPING | 0 |  | 0 | 0 |  | #DIV/0!
30 | Tree Trim and Root Prune | EA | 0 | LANDSCAPING | 0 |  | 0 | 0 |  | #DIV/0!

## Labor Budget
PROJECT: | SW62
LOCATION: | 1st St
INITIAL REPORT: | 2025-06-24
COST CODE SUMMARY
Cost Code | QTY | UOM | Est HRS | Material | Notes | Hauling |  | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17
DEMO/EX | 72.4193 | CY | 59.5119 |  |  | 8.6903 |  | 48 | Day 1: 32; Day 2: 16
BASE/GRADING | 35.5746 | CY | 35.5746 |  |  |  |  | 16 | Day 2: 16
CONCRETE | 32.9365 | CY | 164.6824 |  |  |  |  | 80 | Day 3: 40; Day 4: 40
AC | 5.4792 | TON | 5.4792 |  |  |  |  | 24 | Day 5: 24
MOB/DEMOB |  |  | ?? |  |  |  |  | 0
GENERAL LABOR |  |  | ?? |  |  |  |  | 16 | Day 3: 8; Day 4: 8
TRAFFIC CONTROL |  |  | ?? |  |  |  |  | 0
LANDSCAPING |  |  | ?? |  |  |  |  | 0
UTILITY ADJ |  |  | 0 |  |  |  |  | 0
HAULING | [7 empty] | 40 | Day 1: 20; Day 2: 10; Day 5: 10
|  |  | 265.2482 |  |  |  |  | 224
TC/GL Labor Usage
Cost Code | QTY | UOM | Est HRS | Crew Size | Crew Days | TC HRS | GL HRS
DEMO/EX | 72.4193 | CY | 59.5119 | 2 | 3.7195 | 59.5119 | 59.5119
BASE/GRADING | 35.5746 | CY | 35.5746 | 2 | 2.2234 | 35.5746 | 35.5746
CONCRETE | 32.9365 | CY | 164.6824 | 2 | 10.2927 | 164.6824 | 164.6824
AC | 5.4792 | TON | 5.4792 | 2 | 0.34245 | 5.4792 | 5.4792
[5 empty] | Total | 265.2482 | 265.2482
CONCRETE SUMMARY
| CY | Est HRS | Crew Size | Crew Days | TC HRS | GL HRS
ALL CURB AND GUTTER | 6.28 | 31.38 | 0 | #DIV/0! | 31.38 | 31.38
OTHER | 21.56 | 107.81 | 0 | #DIV/0! | 107.81 | 107.81
Totals | 27.84 | 139.19 |  | #DIV/0! | 139.19 | 139.19
MISC |  |  |  |  | HAULING
UTILITY ADJ | QTY | UOM | HRS |  | CY DEMO/EX | 72.4193
|  | EA | 0 |  | LOADS | 8.6903
|  | EA | 0 |  | HRS | 26.0709
LANDSCAPING
LF
EA