## Sheet1
LINE ITEM | SLATER | UNIT | QTY | UNIT COST | UNIT TOTAL | COST CODE | UM | ACTUAL | QTY | PX | HRS | LBR COST | EQUIP | TRUCKING | DUMP FEES | MATERIAL | SUB | TOTAL | DIFFERENCE
25 | Asphalt Concrete Pavement | TON | 158 | 400 | 63200 | AC | TON |  | 158 | 1 | 158 | 14220 |  |  |  | 15010 | $- | 29230 | 33970
25.1 | Asphalt Concrete Pavement | SF | 4160.54 |  |  | AC | TON |  | 154.0941 | 1
2 | Allowance for Differing Site Conditions per General Requirements, Sections 01212 & 01253 | LS | 1 | 10000 | 10000 | ALLOWANCE |  |  | 1 | [8 empty] | $- | 10000
3 | Allowance for Grading in Temporary Construction Easement per General Requirements, Section 01212 | LS | 1 | 15000 | 15000 | ALLOWANCE |  |  | 1 | [8 empty] | $- | 15000
4 | Allowance for Railroad Requirements for Safety Plan, Permitting, Flagging, and Inspection | LS | 1 | 35000 | 35000 | ALLOWANCE |  |  | 1 |  | 0 | $- |  |  |  | $- |  | $- | 35000
26 | Crushed Miscellaneous Base | CY | 101.3366 | 250 | 36250 | BASE/GRADING |  |  | 101.3366 | 1 | 145 | 13050 |  |  |  | 5800 |  | 18850 | 17400
26.1 | Concrete Curb Type A | LF | 79 |  |  | BASE/GRADING | CY |  | 1.463 | 1 | 9
26.2 | Concrete Integral Curb and Gutter, Type To Be Specified Per Plan (a=2', b=6") | LF | 317 |  |  | BASE/GRADING | CY |  | 45.2857 | 1 | 272
26.3 | Concrete Intersection Gutter (b=6", g=4', v=varies) | SF | 384 |  |  | BASE/GRADING | CY |  | 7.1111 | 1 | 29
26.4 | Concrete Driveway (t=6") | SF | 339 |  |  | BASE/GRADING | CY |  | 6.2778 | 1 | 38
26.5 | Concrete Sidewalk (t=4") | SF | 2507 |  |  | BASE/GRADING | CY |  | 31.3375 | 1 | 188
26.6 | Curb Ramp, including Detectable Warning Surface | EA | 4 |  |  | BASE/GRADING | CY |  | 8 | 1 | 48
26.7 | Nonwalkable Surface | SF | 23 |  |  | BASE/GRADING | CY |  | 0.2875 | 1 | 2
26.8 | Concrete Wall, including Chain Link Fence | LF | 85 |  |  | BASE/GRADING | CY |  | 1.5741 | 1 | 9
26.9 | Asphalt Concrete Pavement | SF |  |  |  | BASE/GRADING | CY |  | 0 | 1
19 | Concrete Curb Type A | LF | 79 | 80 | 6320 | CONCRETE | CY |  | 1.463 | 6 | 9 | 702.22 | $- | $- | $- | 329.17 |  | 1031.39 | 5288.61
20 | Concrete Integral Curb and Gutter, Type To Be Specified Per Plan (a=2', b=6") | LF | 317 | 150 | 47550 | CONCRETE | CY |  | 45.2857 | 6 | 272 | 21737.14 |  |  |  | 10189.29 |  | 31926.43 | 15623.57
21 | Concrete Intersection Gutter (b=6", g=4', v=varies) | SF | 384 | 25 | 9600 | CONCRETE | CY |  | 7.1111 | 6 | 29 | 2304 |  |  |  | 1080 |  | 3384 | 6216
22 | Concrete Driveway (t=6") | SF | 339 | 20 | 6780 | CONCRETE | CY |  | 6.2778 | 6 | 38 | 3013.33 |  |  |  | 1412.5 |  | 4425.83 | 2354.17
23 | Concrete Sidewalk (t=4") | SF | 2507 | 20 | 50140 | CONCRETE | CY |  | 31.3375 | 6 | 188 | 15042 |  |  |  | 7050.94 |  | 22092.94 | 28047.06
24 | Curb Ramp, including Detectable Warning Surface | EA | 4 | 12000 | 48000 | CONCRETE | CY |  | 8 | 6 | 48 | 3840 |  |  |  | 1800 |  | 5640 | 42360
27 | Nonwalkable Surface | SF | 23 | 50 | 1150 | CONCRETE | CY |  | 0.2875 | 6 | 2 | 138 |  |  |  | 64.69 |  | 202.69 | 947.31
32 | Concrete Wall, including Chain Link Fence | LF | 85 | 300 | 25500 | CONCRETE | CY |  | 1.5741 | 6 | 9 | 755.56 | 7225 |  |  | 354.17 |  | 8334.72 | 17165.28
6 | Concrete Curb | LF | 21 | 25 | 525 | DEMO/EX | CY |  | 0.38889 | 1 | 0 | 31.11 |  | 13.61 | 13.61 |  |  | 58.33 | 466.67
7 | Concrete Integral Curb and Gutter | LF | 302 | 50 | 15100 | DEMO/EX | CY |  | 20.1333 | 1 | 20 | 1610.67 |  | 704.67 | 704.67 |  |  | 3020 | 12080
8 | Concrete Intersection Gutter | SF | 350 | 30 | 10500 | DEMO/EX | CY |  | 6.4815 | 1 | 10 | 777.78 |  | 340.28 | 340.28 |  |  | 1458.33 | 9041.67
9 | Concrete Pavement | SF | 503 | 15 | 7545 | DEMO/EX | CY |  | 9.3148 | 1 | 9 | 745.19 |  | 326.02 | 326.02 |  |  | 1397.22 | 6147.78
10 | Concrete Driveway | SF | 250 | 15 | 3750 | DEMO/EX | CY |  | 4.6296 | 1 | 5 | 370.37 |  | 162.04 | 162.04 |  |  | 694.44 | 3055.56
11 | Concrete Sidewalk, including Curb Ramps | SF | 1601 | 10 | 16010 | DEMO/EX | CY |  | 20.0125 | 1 | 20 | 1601 |  | 700.44 | 700.44 |  |  | 3001.88 | 13008.13
12 | Asphalt Concrete Pavement | SF | 4208 | 8 | 33664 | DEMO/EX | CY |  | 77.9259 | 1 | 78 | 7013.33 |  | 2727.41 | 2727.41 |  |  | 12468.15 | 21195.85
13 | Cold Mill Asphalt Concrete Pavement (t=2" min.) | SF | 2115 | 10 | 21150 | DEMO/EX | CY |  | 13.3167 | 1.82 | 24 | 1892.8 | 1500 | 455 | 455 |  |  | 4302.8 | 16847.2
14 | Metal Railroad Fencing | LF | 146 | 50 | 7300 | DEMO/EX |  |  | 146 | 0.2 | 29 | 2336 |  | $- | $- |  | 5840 | 8176 | -876
15 | Unclassified Excavation | CY | 140.4606 | 300 | 43200 | DEMO/EX | CY |  | 140.4606 | 1 | 144 | 12960 |  | 5040 | 5040 |  |  | 23040 | 20160
15.1 | Concrete Curb | LF | 21 |  |  | DEMO/EX | CY |  | 0.38889 | 1 | 0
15.2 | Concrete Integral Curb and Gutter | LF | 302 |  |  | DEMO/EX | CY |  | 20.1333 | 1 | 20
15.3 | Concrete Intersection Gutter | SF | 350 |  |  | DEMO/EX | CY |  | 6.4815 | 1 | 10
15.4 | Concrete Pavement | SF | 503 |  |  | DEMO/EX | CY |  | 9.3148 | 1 | 9
15.5 | Concrete Driveway | SF | 250 |  |  | DEMO/EX | CY |  | 4.6296 | 1 | 5
15.6 | Concrete Sidewalk, including Curb Ramps | SF | 1601 |  |  | DEMO/EX | CY |  | 20.0125 | 1 | 20
15.7 | Asphalt Concrete Pavement | SF | 4208 |  |  | DEMO/EX | CY |  | 77.9259 | 1 | 78
15.8 | Metal Railroad Fencing | LF | 146 |  |  | DEMO/EX |  |  | 146 | 0.2 | 29
15.9 | Remove Tree and Stump | EA | 1 |  |  | DEMO/EX |  |  | 1 | 1 | 16
15.1 | Concrete Wall, including Chain Link Fence | LF | 85 |  |  | DEMO/EX | CY |  | 1.5741 | 6 | 9
15.11 | Wrought Iron Fence, including Gates | LF | 35 |  |  | DEMO/EX |  |  | 35 | 0.25 | 9
16 | Remove Tree and Stump | EA | 1 | 2000 | 2000 | DEMO/EX |  |  | 1 | 1 | 16 | 1440 |  |  |  |  | 1700 | 3140 | -1140
17 | Concrete Wall, including Chain Link Fence | LF | 85 | 100 | 8500 | DEMO/EX | CY |  | 1.5741 | 6 | 9 | 755.56 |  |  |  | 354.17 |  | 1109.72 | 7390.28
18 | Wrought Iron Fence, including Gates | LF | 35 | 20 | 700 | DEMO/EX |  |  | 35 | 0.25 | 9 | 700 |  |  |  |  | 595 | 1295 | -595
30 | Detectable Warning Surface Tile | EA | 2 | 1000 | 2000 | GNRL LBR |  |  | 2 | 4 | 8 | 640 |  |  |  | 600 |  | 1240 | 760
31 | Grade Only or Landscaping | SF | 163 | 5 | 815 | GNRL LBR | SF |  | 163 | 8 | 16 | 1280 | [5 empty] | 1280 | -465
35 | Adjust Street Lighting Pullbox to Grade | EA | 2 | 2500 | 5000 | GNRL LBR |  |  | 2 | 4 | 8 | 600 | [5 empty] | 600 | 4400
36 | Adjust Street Light Pole to Grade | EA | 2 | 2500 | 5000 | GNRL LBR |  |  | 2 | 16 | 32 | 1280 | [5 empty] | 1280 | 3720
38 | Adjust Water Valve to Grade | EA | 1 | 1500 | 1500 | GNRL LBR |  |  | 1 | 4 | 4 | 300 | [5 empty] | 300 | 1200
39 | Adjust Sewer Maintenance Hole to Grade | EA | 3 | 1500 | 4500 | GNRL LBR |  |  | 3 | 4 | 12 | 900 | [5 empty] | 900 | 3600
40 | Street Sign (Remove and Reinstall) | EA | 2 | 1000 | 2000 | GNRL LBR |  |  | 2 | 4 | 8 | 600 | [5 empty] | 600 | 1400
41 | SAWCUT | LF |  |  |  | DEMO/EX |  |  | 0 | 20
1 | Mobilization per General Requirements, Sections 01292 & 01721 | LS | 1 | 15000 | 15000 | MOBILIZATION |  |  | 1 | 1 | 80 | 7200 |  |  |  | 3000 |  | 10200 | 4800
28 | Pedestrian Barricade | EA | 3 | 2500 | 7500 | SUB |  |  | 3 | [7 empty] | 6375 | 6375 | 1125
29 | Chain Link Fencing, including Gates | LF | 63 | 250 | 15750 | SUB |  |  | 63 | [7 empty] | 13387.5 | 13387.5 | 2362.5
33 | Wrought Iron Fence, including Gates | LF | 25 | 300 | 7500 | SUB |  |  | 25 | [7 empty] | 6375 | 6375 | 1125
34 | Signage and Striping per Contract Plans and Documents | LS | 1 | 18000 | 18000 | SUB |  |  | 1 | [7 empty] | 15300 | 15300 | 2700
37 | Street Lighting per Contract Plans and Documents | LS | 1 | 30000 | 30000 | SUB |  |  | 1 | [7 empty] | 25500 | 25500 | 4500
5 | Traffic Control (Includes plan, preparation, implementation, and permitting for all detour and construction stages) | LS | 1 | 70000 | 70000 | TRAFFIC CONTROL |  |  | 4 |  | 192 | 15360 |  |  |  | 15000 |  | 30360 | 39640