## Sheet1
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Descoped | Delayed | Additional | PROJECTED TOTAL | Complete | Remaining | Notes
DEMO/EXCAVATION
76 | SAWCUT | LF | 228 |  |  |  | 228
12 | Unclassified Excavation, including Haul Away | CY |  |  |  |  | 0
12.1 | Concrete Integral Curb & Gutter | LF | 125.5 |  |  |  | 125.5
12.2 | Remove Concrete Sidewalk including Curb Ramp & Driveway | SF | 1520.55 |  |  |  | 1520.55
12.3 | Remove Concrete Curb Type "A" | LF |  |  |  |  | 0
12.4 | Remove 5" Asphalt Concrete | SF | 1905.13 |  |  |  | 1905.13
12.5 | Remove 9" Concrete Pavement | SF |  |  |  |  | 0
7 | Concrete Integral Curb & Gutter | LF | 125.5 |  |  |  | 125.5
8 | Remove Concrete Sidewalk including Curb Ramp & Driveway | SF | 906.67 |  |  |  | 906.67
9 | Remove Concrete Curb Type "A" | LF |  |  |  |  | 0
10 | Remove 5" Asphalt Concrete | SF | 1905.13 |  |  |  | 1905.13
11 | Remove 9" Concrete Pavement | SF |  |  |  |  | 0
13 | Cold Plane (Mill) AC Pavement, 2" Minimum | SF |  |  |  |  | 0 |  |  | Grind and Overlay is a separate phase
BASE/GRADING
15 | Crushed Miscellaneous Base, Varies 4", 6" or 8" | CY |  |  |  |  | 0
15.1 | Concrete Sidewalk (t=4") | SF | 2048.36 |  |  |  | 2048.36
15.2 | Type C - Integral Curb & Gutter (a=2' to 4', b=8") including Warped Gutter at Catch Basin | LF | 136.5 |  |  |  | 136.5
15.3 | Concrete Curb Type "A" | LF | 9 |  |  |  | 9
15.4 | Concrete Intersection Gutter (b=8", g=4' to 5') | SF | 186.14 |  |  |  | 186.14
15.5 | Concrete Driveway (t=6") | SF |  |  |  |  | 0
15.6 | Concrete Curb Ramp | SF | 164.51 |  |  |  | 164.51
15.7 | Concrete Pavement (t=8") including Bus Pad & Median Island | SF | 1002.23 |  |  |  | 1002.23
15.8 | Detectable Warning Surface | SF | 24 |  |  |  | 24
15.9 | Doweled Curb | LF |  |  |  |  | 0
15.11 | Asphalt Concrete Pavement | SF |  |  |  |  | 0
CONCRETE
14 | Concrete Sidewalk (t=4") | SF | 2048.36 |  |  |  | 2048.36
16 | Type C - Integral Curb & Gutter (a=2' to 4', b=8") including Warped Gutter at Catch Basin | LF | 136.5 |  |  |  | 136.5
17 | Concrete Curb Type "A" | LF | 9 |  |  |  | 9
18 | Concrete Intersection Gutter (b=8", g=4' to 5') | SF | 186.14 |  |  |  | 186.14
19 | Concrete Driveway (t=6") | SF |  |  |  |  | 0
20 | Concrete Curb Ramp | EA | 2 |  |  |  | 2
21 | Concrete Pavement (t=8") including Bus Pad & Median Island | SF | 1002.23 |  |  |  | 1002.23
25 | Detectable Warning Surface | SF | 24 |  |  |  | 24
26 | Doweled Curb | LF |  |  |  |  | 0
ASPHALT
22 | Asphalt Concrete Pavement | TON |  |  |  |  | 0
22.1 | Asphalt Concrete Pavement | SF |  |  |  |  | 0
23 | Variable Thickness Asphalt Concrete Pavement, t=2" minimum | TON |  |  |  |  | 0
23.1 | Variable Thickness Asphalt Concrete Pavement, t=2" minimum | SF |  |  |  |  | 0
UTILITY ADJUSTMENT/OTHER
24 | Grass (SOD) | SF | 361.25 |  |  |  | 361.25
27 | Curb Drain (Schedule 80 PVC Pipe) | EA | 3 |  |  |  | 3
29 | Adjust Bus Bench to Grade | EA |  |  |  |  | 0
30 | Tree Wells at Sidewalk | EA | 2 |  |  |  | 2
31 | Tree Wells at Median Island | EA |  |  |  |  | 0
32 | Adjust and/or relocate Water Valve to Grade | EA | 1 |  |  |  | 1
33 | Adjust and/or relocate Water Meter to Grade | EA | 1 |  |  |  | 1
34 | Adjust and/or relocate Maintenance Hole to Grade | EA |  |  |  |  | 0
75 | Adjust and/or relocate Utility | EA | 2 |  |  |  | 2

## full location
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Actuals | Unit Cost | Unit Total | Cost Code | UM | QTY | PX | HRS | LBR COST | EQUIP | TRUCKING | DUMP FEES | MATERIAL | SUB | BUDGET | BILLINGS
| DEMO/EXCAVATION | [16 empty] | 0 | 0
76 | SAWCUT | LF | 228 |  |  | 0 | DEMO/EX | CY | 0.57 | 20 | 11.4 | 30720 | [5 empty] | 30720 | 0
12 | Unclassified Excavation, including Haul Away | CY | 65.67 |  | 240 | 15760.8 | DEMO/EX | CY | 56.6832 | 1 | 56.6832 | 45360 |  | 17640 | 17640 |  |  | 80640 | 15760.8
12.1 | Concrete Integral Curb & Gutter | LF | 125.5 |  |  | 0 | DEMO/EX | CY | 8.3667 | 1 | 8.3667 | [6 empty] | 0 | 0
12.2 | Remove Concrete Sidewalk including Curb Ramp & Driveway | SF | 1520.55 |  |  | 0 | DEMO/EX | CY | 19.0069 | 1 | 19.0069 | [6 empty] | 0 | 0
12.3 | Remove Concrete Curb Type "A" | LF |  |  |  | 0 | DEMO/EX | CY | 0 | 1 | 0 | [6 empty] | 0 | 0
12.4 | Remove 5" Asphalt Concrete | SF | 1905.13 |  |  | 0 | DEMO/EX | CY | 29.3097 | 1 | 29.3097 | [6 empty] | 0 | 0
12.5 | Remove 9" Concrete Pavement | SF |  |  |  | 0 | DEMO/EX | CY | 0 | 1 | 0 | [6 empty] | 0 | 0
7 | Concrete Integral Curb & Gutter | LF | 125.5 |  | 40 | 5020 | DEMO/EX | CY | 8.3667 | 1 | 8.3667 | 7302 |  | 2839.67 | 2839.67 |  |  | 12981.34 | 5020
8 | Remove Concrete Sidewalk including Curb Ramp & Driveway | SF | 906.67 |  | 9 | 8160.03 | DEMO/EX | CY | 11.3334 | 1 | 11.3334 | 15647.63 |  | 6085.19 | 6085.19 |  |  | 27818.01 | 8160.03
9 | Remove Concrete Curb Type "A" | LF |  |  | 25 | 0 | DEMO/EX | CY | 0 | 1 | 0 | 141.67 |  | 55.09 | 55.09 |  |  | 251.85 | 0
10 | Remove 5" Asphalt Concrete | SF | 1905.13 |  | 6.5 | 12383.345 | DEMO/EX | CY | 29.3097 | 1 | 29.3097 | 42860.77 |  | 16668.08 | 16668.08 |  |  | 76196.93 | 12383.345
11 | Remove 9" Concrete Pavement | SF |  |  | 10 | 0 | DEMO/EX | CY | 0 | 1 | 0 | 77387.5 |  | 30095.14 | 30095.14 |  |  | 137577.78 | 0
13 | Cold Plane (Mill) AC Pavement, 2" Minimum | SF |  |  | 4 | 0 | DEMO/EX | CY | 0 |  | 0 | $- | [5 empty] | 0 | 0
| BASE/GRADING | [16 empty] | 0 | 0
15 | Crushed Miscellaneous Base, Varies 4", 6" or 8" | CY | 75.91 |  | 170 | 12904.7 | BASE/GRADING | CY | 65.0938 | 0.75 | 48.8204 | 72090 | [5 empty] | 72090 | 12904.7
15.1 | Concrete Sidewalk (t=4") | SF | 2048.36 |  |  | 0 | BASE/GRADING | CY | 25.6045 | 0.75 | 19.2034 | [6 empty] | 0 | 0
15.2 | Type C - Integral Curb & Gutter (a=2' to 4', b=8") including Warped Gutter at Catch Basin | LF | 136.5 |  |  | 0 | BASE/GRADING | CY | 9.1 | 0.75 | 6.825 | [6 empty] | 0 | 0
15.3 | Concrete Curb Type "A" | LF | 9 |  |  | 0 | BASE/GRADING | CY | 0.16667 | 0.75 | 0.125 | [6 empty] | 0 | 0
15.4 | Concrete Intersection Gutter (b=8", g=4' to 5') | SF | 186.14 |  |  | 0 | BASE/GRADING | CY | 3.447 | 0.75 | 2.5853 | [6 empty] | 0 | 0
15.5 | Concrete Driveway (t=6") | SF |  |  |  | 0 | BASE/GRADING | CY | 0 | 0.75 | 0 | [6 empty] | 0 | 0
15.6 | Concrete Curb Ramp | SF | 164.51 |  |  | 0 | BASE/GRADING | CY | 2.031 | 0.75 | 1.5232 | [6 empty] | 0 | 0
15.7 | Concrete Pavement (t=8") including Bus Pad & Median Island | SF | 1002.23 |  |  | 0 | BASE/GRADING | CY | 24.4446 | 0.75 | 18.3335 | [6 empty] | 0 | 0
15.8 | Detectable Warning Surface | SF | 24 |  |  | 0 | BASE/GRADING | CY | 0.3 | 0.75 | 0.225 | [6 empty] | 0 | 0
15.9 | Doweled Curb | LF |  |  |  | 0 | BASE/GRADING | CY | 0 | 0.75 | 0 | [6 empty] | 0 | 0
15.11 | Asphalt Concrete Pavement | SF |  |  |  | 0 | BASE/GRADING | CY | 0 | 0.75 | 0 | [6 empty] | 0 | 0
| CONCRETE | [16 empty] | 0 | 0
14 | Concrete Sidewalk (t=4") | SF | 2048.36 |  | 18 | 36870.48 | CONCRETE | CY | 25.6045 | 6 | 153.627 | 119691 | [5 empty] | 119691 | 36870.48
16 | Type C - Integral Curb & Gutter (a=2' to 4', b=8") including Warped Gutter at Catch Basin | LF | 136.5 |  | 75 | 10237.5 | CONCRETE | CY | 11.375 | 6 | 68.25 | [6 empty] | 0 | 10237.5
17 | Concrete Curb Type "A" | LF | 9 |  | 70 | 630 | CONCRETE | CY | 0.16667 | 6 | 1 | 560 | [5 empty] | 560 | 630
18 | Concrete Intersection Gutter (b=8", g=4' to 5') | SF | 186.14 |  | 20 | 3722.8 | CONCRETE | CY | 3.447 | 6 | 20.6822 | 30222.22 | [5 empty] | 30222.22 | 3722.8
19 | Concrete Driveway (t=6") | SF |  |  | 20 | 0 | CONCRETE | CY | 0 | 6 | 0 | 10360 | [5 empty] | 10360 | 0
20 | Concrete Curb Ramp | EA | 2 |  | 7000 | 14000 | CONCRETE | CY | 4 | 4 | 16 | [6 empty] | 0 | 14000
21 | Concrete Pavement (t=8") including Bus Pad & Median Island | SF | 1002.23 |  | 20 | 20044.6 | CONCRETE | CY | 24.4446 | 6 | 146.6678 | 110186.34 | [5 empty] | 110186.34 | 20044.6
25 | Detectable Warning Surface | SF | 24 |  | 60 | 1440 | CONCRETE | CY | 0.3 | 6 | 1.8 | 1296 | [5 empty] | 1296 | 1440
26 | Doweled Curb | LF |  |  | 70 | 0 | CONCRETE | CY | 0 | 6 | 0 | 14711.11 | [5 empty] | 14711.11 | 0
| ASPHALT | [16 empty] | 0 | 0
22 | Asphalt Concrete Pavement | TON |  |  | 280 | 0 | AC | TON | 0 | 0.75 | 0 | 70942.5 | [5 empty] | 70942.5 | 0
22.1 | Asphalt Concrete Pavement | SF |  |  |  | 0 | AC | TON | 0 | 0.75 | 0 | [6 empty] | 0 | 0
23 | Variable Thickness Asphalt Concrete Pavement, t=2" minimum | TON |  |  | 300 | 0 | AC | TON | 0 | 0.75 | 0 | 54000 | [5 empty] | 54000 | 0
23.1 | Variable Thickness Asphalt Concrete Pavement, t=2" minimum | SF |  |  |  | 0 | AC | TON | 0 | 0.75 | 0 | [6 empty] | 0 | 0
| UTILITY ADJUSTMENT/OTHER | [16 empty] | 0 | 0
24 | Grass (SOD) | SF | 361.25 |  | 10 | 3612.5 | GNRL LBR |  | 361.25 | 20 | 7225 | 1276 | [5 empty] | 1276 | 3612.5
27 | Curb Drain (Schedule 80 PVC Pipe) | EA | 3 |  | 1500 | 4500 | GNRL LBR |  | 3 | 4 | 12 | 960 | [5 empty] | 960 | 4500
29 | Adjust Bus Bench to Grade | EA |  |  | 800 | 0 | GNRL LBR |  | 0 | 4 | 0 | 320 | [5 empty] | 320 | 0
30 | Tree Wells at Sidewalk | EA | 2 |  | 1000 | 2000 | GNRL LBR |  | 2 | 4 | 8 | 1600 | [5 empty] | 1600 | 2000
31 | Tree Wells at Median Island | EA |  |  | 1000 | 0 | GNRL LBR |  | 0 | 4 | 0 | 2240 | [5 empty] | 2240 | 0
32 | Adjust and/or relocate Water Valve to Grade | EA | 1 |  | 500 | 500 | GNRL LBR |  | 1 | 4 | 4 | 5440 | [5 empty] | 5440 | 500
33 | Adjust and/or relocate Water Meter to Grade | EA | 1 |  | 3500 | 3500 | GNRL LBR |  | 1 | 4 | 4 | 2560 | [5 empty] | 2560 | 3500
34 | Adjust and/or relocate Maintenance Hole to Grade | EA |  |  | 3500 | 0 | GNRL LBR |  | 0 | 8 | 0 | 3200 | [5 empty] | 3200 | 0
75 | Adjust and/or relocate Utility | EA | 2 |  |  | 0 | GNRL LBR |  | 2 | 4 | 8 | [6 empty] | 0 | 0
155286.755
| COST CODE | PX |  | ACTUAL HRS
| DEMO/EX | 20
| BASE/GRADING | 0.75
| CONCRETE | 6
| AC | 0.75
Update PX Rates
Create Final Reports

## Filtered Rows
HSIP - 76th and Crenshaw - NW Corner
DEMO/EX
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Cost Code | CY | PX | HRS | MD | CREW SIZE | CREW DAYS
76 | SAWCUT | LF | 228 | DEMO/EX | 0.57 | 20 | 11.4 | 1.425 |  | #DIV/0!
12.1 | Concrete Integral Curb & Gutter | LF | 125.5 | DEMO/EX | 8.3667 | 1 | 8.3667 | 1.0458 |  | #DIV/0!
12.2 | Remove Concrete Sidewalk including Curb Ramp & Driveway | SF | 1520.55 | DEMO/EX | 19.0069 | 1 | 19.0069 | 2.3759 |  | #DIV/0!
12.3 | Remove Concrete Curb Type "A" | LF |  | DEMO/EX | 0 | 1 | 0 | 0 |  | #DIV/0!
12.4 | Remove 5" Asphalt Concrete | SF | 1905.13 | DEMO/EX | 29.3097 | 1 | 29.3097 | 3.6637 |  | #DIV/0!
12.5 | Remove 9" Concrete Pavement | SF |  | DEMO/EX | 0 | 1 | 0 | 0 |  | #DIV/0!
7 | Concrete Integral Curb & Gutter | LF | 125.5 | DEMO/EX | 8.3667 | 1 | 8.3667 | 1.0458 |  | #DIV/0!
8 | Remove Concrete Sidewalk including Curb Ramp & Driveway | SF | 906.67 | DEMO/EX | 11.3334 | 1 | 11.3334 | 1.4167 |  | #DIV/0!
9 | Remove Concrete Curb Type "A" | LF |  | DEMO/EX | 0 | 1 | 0 | 0 |  | #DIV/0!
10 | Remove 5" Asphalt Concrete | SF | 1905.13 | DEMO/EX | 29.3097 | 1 | 29.3097 | 3.6637 |  | #DIV/0!
11 | Remove 9" Concrete Pavement | SF |  | DEMO/EX | 0 | 1 | 0 | 0 |  | #DIV/0!
13 | Cold Plane (Mill) AC Pavement, 2" Minimum | SF |  | DEMO/EX | 0 |  | 0 | 0 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | DEMO/EX | 106.263 |  | 117.093 | 14.6366 | #DIV/0! | #DIV/0!
BASE/GRADING
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Cost Code | CY | PX | HRS | MD | CREW SIZE | CREW DAYS
15.1 | Concrete Sidewalk (t=4") | SF | 2048.36 | BASE/GRADING | 25.6045 | 0.75 | 19.2034 | 2.4004 |  | #DIV/0!
15.2 | Type C - Integral Curb & Gutter (a=2' to 4', b=8") including Warped Gutter at Catch Basin | LF | 136.5 | BASE/GRADING | 9.1 | 0.75 | 6.825 | 0.85312 |  | #DIV/0!
15.3 | Concrete Curb Type "A" | LF | 9 | BASE/GRADING | 0.16667 | 0.75 | 0.125 | 0.015625 |  | #DIV/0!
15.4 | Concrete Intersection Gutter (b=8", g=4' to 5') | SF | 186.14 | BASE/GRADING | 3.447 | 0.75 | 2.5853 | 0.32316 |  | #DIV/0!
15.5 | Concrete Driveway (t=6") | SF |  | BASE/GRADING | 0 | 0.75 | 0 | 0 |  | #DIV/0!
15.6 | Concrete Curb Ramp | SF | 164.51 | BASE/GRADING | 2.031 | 0.75 | 1.5232 | 0.19041 |  | #DIV/0!
15.7 | Concrete Pavement (t=8") including Bus Pad & Median Island | SF | 1002.23 | BASE/GRADING | 24.4446 | 0.75 | 18.3335 | 2.2917 |  | #DIV/0!
15.8 | Detectable Warning Surface | SF | 24 | BASE/GRADING | 0.3 | 0.75 | 0.225 | 0.028125 |  | #DIV/0!
15.9 | Doweled Curb | LF |  | BASE/GRADING | 0 | 0.75 | 0 | 0 |  | #DIV/0!
15.11 | Asphalt Concrete Pavement | SF |  | BASE/GRADING | 0 | 0.75 | 0 | 0 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | BASE/GRADING | 65.0938 |  | 48.8204 | 6.1025 | #DIV/0! | #DIV/0!
CONCRETE
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Cost Code | CY | PX | HRS | MD | CREW SIZE | CREW DAYS
14 | Concrete Sidewalk (t=4") | SF | 2048.36 | CONCRETE | 25.6045 | 5 | 128.0225 | 16.0028 |  | #DIV/0!
16 | Type C - Integral Curb & Gutter (a=2' to 4', b=8") including Warped Gutter at Catch Basin | LF | 136.5 | CONCRETE | 11.375 | 5 | 56.875 | 7.1094 |  | #DIV/0!
17 | Concrete Curb Type "A" | LF | 9 | CONCRETE | 0.16667 | 5 | 0.83333 | 0.10417 |  | #DIV/0!
18 | Concrete Intersection Gutter (b=8", g=4' to 5') | SF | 186.14 | CONCRETE | 3.447 | 5 | 17.2352 | 2.1544 |  | #DIV/0!
19 | Concrete Driveway (t=6") | SF |  | CONCRETE | 0 | 5 | 0 | 0 |  | #DIV/0!
20 | Concrete Curb Ramp | EA | 2 | CONCRETE | 4 | 5 | 20 | 2.5 |  | #DIV/0!
21 | Concrete Pavement (t=8") including Bus Pad & Median Island | SF | 1002.23 | CONCRETE | 24.4446 | 5 | 122.2232 | 15.2779 |  | #DIV/0!
25 | Detectable Warning Surface | SF | 24 | CONCRETE | 0.3 | 5 | 1.5 | 0.1875 |  | #DIV/0!
26 | Doweled Curb | LF |  | CONCRETE | 0 | 5 | 0 | 0 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | CONCRETE | 69.3378 |  | 346.6892 | 43.3361 | #DIV/0! | #DIV/0!
AC
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Cost Code | TON | PX | HRS | MD | CREW SIZE | CREW DAYS
22.1 | Asphalt Concrete Pavement | SF |  | AC | 0 | 0.75 | 0 | 0 |  | #DIV/0!
23.1 | Variable Thickness Asphalt Concrete Pavement, t=2" minimum | SF |  | AC | 0 | 0.75 | 0 | 0 |  | #DIV/0!
|  |  |  | TOTALS | QTY |  | HRS | MD | CREW SIZE | CREW DAYS
|  |  |  | AC | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
UTILITY ADJ
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Cost Code | QTY | PX | HRS | MD | CREW SIZE | CREW DAYS
LANDSCAPING
Line Item | HSIP - 76th and Crenshaw - NW Corner | Unit | QTY | Cost Code | QTY | PX | HRS | MD | CREW SIZE | CREW DAYS

## Summary
HSIP - 76th and Crenshaw - NW Corner
Cost Code | QTY | UOM | Est HRS | Man Days | Crew Size | Crew Days
DEMO/EX | 106.263 | CY | 117.093 | 14.6366 | 0 | #DIV/0!
BASE/GRADING | 65.0938 | CY | 48.8204 | 6.1025 | 0 | #DIV/0!
CONCRETE | 69.3378 | CY | 346.6892 | 43.3361 | 0 | #DIV/0!
AC | 0 | TON | 0 | 0 | 0 | #DIV/0!
UTILITY ADJ | Unit | QTY
LANDSCAPING | Unit | QTY